## Gantt Chart
AIvsAI-SOC – Red vs Blue AI Retail Security Platform ¦ Agile Gantt Chart ¦ Jul 21, 2026 – Nov 4, 2026 (107 Days)
Task / Phase | Dur. | Start Date | End Date | Sprint | Status | July 2026 | [10 empty] | August 2026 | [30 empty] | September 2026 | [29 empty] | October 2026 | [30 empty] | Nov 2026 |  |  |  | Status | Sprint | End Date | Start Date | Dur. | Task / Phase
[6 empty] | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W
[6 empty] | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4
Sprint 0: Project Setup & Planning | 7 | 2026-07-21 | 2026-07-27 | Sprint 0 | complete | July 2026 T 21: Sprint 0: Project Setup & Planning | complete | Sprint 0 | 2026-07-27 | 2026-07-21 | 7 | Sprint 0: Project Setup & Planning
Project Kickoff Meeting | 1 | 2026-07-21 | 2026-07-21 |  | complete | [107 empty] | complete |  | 2026-07-21 | 2026-07-21 | 1 | Project Kickoff Meeting | bar: July 2026 T 21 to July 2026 F 24; July 2026 M 27 to July 2026 F 31; August 2026 M 3 to August 2026 F 7; August 2026 M 10 to August 2026 F 14; August 2026 M 17 to August 2026 F 21; August 2026 M 24 to August 2026 F 28; August 2026 M 31 to September 2026 F 4; September 2026 M 7 to September 2026 F 11; September 2026 M 14 to September 2026 F 18; September 2026 M 21 to September 2026 F 25; September 2026 M 28 to October 2026 F 2; October 2026 M 5 to October 2026 F 9; October 2026 M 12 to October 2026 F 16; October 2026 M 19 to October 2026 F 23; October 2026 M 26 to October 2026 F 30; Nov 2026 M 2 to Nov 2026 W 4
Requirements & Threat Modelling | 2 | 2026-07-22 | 2026-07-23 |  | complete | [107 empty] | complete |  | 2026-07-23 | 2026-07-22 | 2 | Requirements & Threat Modelling | bar: July 2026 W 22 to July 2026 T 23
Dev Environment Setup (MERN) | 2 | 2026-07-24 | 2026-07-25 |  | complete | [107 empty] | complete |  | 2026-07-25 | 2026-07-24 | 2 | Dev Environment Setup (MERN) | bar: July 2026 T 21 to July 2026 S 25; July 2026 M 27 to July 2026 F 31; August 2026 M 3 to August 2026 F 7; August 2026 M 10 to August 2026 F 14; August 2026 M 17 to August 2026 F 21; August 2026 M 24 to August 2026 F 28; August 2026 M 31 to September 2026 F 4; September 2026 M 7 to September 2026 F 11; September 2026 M 14 to September 2026 F 18; September 2026 M 21 to September 2026 F 25; September 2026 M 28 to October 2026 F 2; October 2026 M 5 to October 2026 F 9; October 2026 M 12 to October 2026 F 16; October 2026 M 19 to October 2026 F 23; October 2026 M 26 to October 2026 F 30; Nov 2026 M 2 to Nov 2026 W 4
Database Schema Design | 2 | 2026-07-26 | 2026-07-27 |  | complete | [107 empty] | complete |  | 2026-07-27 | 2026-07-26 | 2 | Database Schema Design | bar: July 2026 S 26 to July 2026 M 27
Sprint 1: Authentication & User Mgmt | 14 | 2026-07-28 | 2026-08-10 | Sprint 1 | complete | July 2026 T 28: Sprint 1: Authentication & User Mgmt | complete | Sprint 1 | 2026-08-10 | 2026-07-28 | 14 | Sprint 1: Authentication & User Mgmt
UI Design: Login & Signup Pages | 2 | 2026-07-28 | 2026-07-29 |  | complete | [107 empty] | complete |  | 2026-07-29 | 2026-07-28 | 2 | UI Design: Login & Signup Pages | bar: July 2026 T 28 to July 2026 W 29
Signup & Login (JWT + bcrypt) | 3 | 2026-07-30 | 2026-08-01 |  | complete | [107 empty] | complete |  | 2026-08-01 | 2026-07-30 | 3 | Signup & Login (JWT + bcrypt) | bar: July 2026 T 21 to July 2026 F 24; July 2026 M 27 to August 2026 S 1; August 2026 M 3 to August 2026 F 7; August 2026 M 10 to August 2026 F 14; August 2026 M 17 to August 2026 F 21; August 2026 M 24 to August 2026 F 28; August 2026 M 31 to September 2026 F 4; September 2026 M 7 to September 2026 F 11; September 2026 M 14 to September 2026 F 18; September 2026 M 21 to September 2026 F 25; September 2026 M 28 to October 2026 F 2; October 2026 M 5 to October 2026 F 9; October 2026 M 12 to October 2026 F 16; October 2026 M 19 to October 2026 F 23; October 2026 M 26 to October 2026 F 30; Nov 2026 M 2 to Nov 2026 W 4
Admin Login Module | 2 | 2026-08-02 | 2026-08-03 |  | complete | [107 empty] | complete |  | 2026-08-03 | 2026-08-02 | 2 | Admin Login Module | bar: August 2026 S 2 to August 2026 M 3
Role-Based Access Control (RBAC) | 2 | 2026-08-04 | 2026-08-05 |  | complete | [107 empty] | complete |  | 2026-08-05 | 2026-08-04 | 2 | Role-Based Access Control (RBAC) | bar: July 2026 T 21 to July 2026 F 24; July 2026 M 27 to July 2026 F 31; August 2026 M 3 to August 2026 F 7; August 2026 M 10 to August 2026 F 14; August 2026 M 17 to August 2026 F 21; August 2026 M 24 to August 2026 F 28; August 2026 M 31 to September 2026 F 4; September 2026 M 7 to September 2026 F 11; September 2026 M 14 to September 2026 F 18; September 2026 M 21 to September 2026 F 25; September 2026 M 28 to October 2026 F 2; October 2026 M 5 to October 2026 F 9; October 2026 M 12 to October 2026 F 16; October 2026 M 19 to October 2026 F 23; October 2026 M 26 to October 2026 F 30; Nov 2026 M 2 to Nov 2026 W 4
User Profile Page | 3 | 2026-08-06 | 2026-08-08 |  | complete | [107 empty] | complete |  | 2026-08-08 | 2026-08-06 | 3 | User Profile Page | bar: August 2026 T 6 to August 2026 S 8
Manage Users Module (Admin) | 2 | 2026-08-09 | 2026-08-10 |  | complete | [107 empty] | complete |  | 2026-08-10 | 2026-08-09 | 2 | Manage Users Module (Admin) | bar: July 2026 T 21 to July 2026 F 24; July 2026 M 27 to July 2026 F 31; August 2026 M 3 to August 2026 F 7; August 2026 S 9 to August 2026 F 14; August 2026 M 17 to August 2026 F 21; August 2026 M 24 to August 2026 F 28; August 2026 M 31 to September 2026 F 4; September 2026 M 7 to September 2026 F 11; September 2026 M 14 to September 2026 F 18; September 2026 M 21 to September 2026 F 25; September 2026 M 28 to October 2026 F 2; October 2026 M 5 to October 2026 F 9; October 2026 M 12 to October 2026 F 16; October 2026 M 19 to October 2026 F 23; October 2026 M 26 to October 2026 F 30; Nov 2026 M 2 to Nov 2026 W 4
Sprint 2: Storefront, Cart & Orders | 14 | 2026-08-11 | 2026-08-24 | Sprint 2 | complete | August 2026 T 11: Sprint 2: Storefront, Cart & Orders | complete | Sprint 2 | 2026-08-24 | 2026-08-11 | 14 | Sprint 2: Storefront, Cart & Orders
Storefront UI Design (Home) | 2 | 2026-08-11 | 2026-08-12 |  | complete | [107 empty] | complete |  | 2026-08-12 | 2026-08-11 | 2 | Storefront UI Design (Home) | bar: July 2026 T 21 to July 2026 F 24; July 2026 M 27 to July 2026 F 31; August 2026 M 3 to August 2026 F 7; August 2026 M 10 to August 2026 F 14; August 2026 M 17 to August 2026 F 21; August 2026 M 24 to August 2026 F 28; August 2026 M 31 to September 2026 F 4; September 2026 M 7 to September 2026 F 11; September 2026 M 14 to September 2026 F 18; September 2026 M 21 to September 2026 F 25; September 2026 M 28 to October 2026 F 2; October 2026 M 5 to October 2026 F 9; October 2026 M 12 to October 2026 F 16; October 2026 M 19 to October 2026 F 23; October 2026 M 26 to October 2026 F 30; Nov 2026 M 2 to Nov 2026 W 4
Product Catalog & Search Pages | 3 | 2026-08-13 | 2026-08-15 |  | complete | [107 empty] | complete |  | 2026-08-15 | 2026-08-13 | 3 | Product Catalog & Search Pages | bar: August 2026 T 13 to August 2026 S 15
Admin Product Mgmt (CRUD, Uploads) | 3 | 2026-08-16 | 2026-08-18 |  | complete | [107 empty] | complete |  | 2026-08-18 | 2026-08-16 | 3 | Admin Product Mgmt (CRUD, Uploads) | bar: July 2026 T 21 to July 2026 F 24; July 2026 M 27 to July 2026 F 31; August 2026 M 3 to August 2026 F 7; August 2026 M 10 to August 2026 F 14; August 2026 S 16 to August 2026 F 21; August 2026 M 24 to August 2026 F 28; August 2026 M 31 to September 2026 F 4; September 2026 M 7 to September 2026 F 11; September 2026 M 14 to September 2026 F 18; September 2026 M 21 to September 2026 F 25; September 2026 M 28 to October 2026 F 2; October 2026 M 5 to October 2026 F 9; October 2026 M 12 to October 2026 F 16; October 2026 M 19 to October 2026 F 23; October 2026 M 26 to October 2026 F 30; Nov 2026 M 2 to Nov 2026 W 4
Shopping Cart Module | 2 | 2026-08-19 | 2026-08-20 |  | complete | [107 empty] | complete |  | 2026-08-20 | 2026-08-19 | 2 | Shopping Cart Module | bar: August 2026 W 19 to August 2026 T 20
Checkout & Order Creation | 2 | 2026-08-21 | 2026-08-22 |  | complete | [107 empty] | complete |  | 2026-08-22 | 2026-08-21 | 2 | Checkout & Order Creation | bar: July 2026 T 21 to July 2026 F 24; July 2026 M 27 to July 2026 F 31; August 2026 M 3 to August 2026 F 7; August 2026 M 10 to August 2026 F 14; August 2026 M 17 to August 2026 S 22; August 2026 M 24 to August 2026 F 28; August 2026 M 31 to September 2026 F 4; September 2026 M 7 to September 2026 F 11; September 2026 M 14 to September 2026 F 18; September 2026 M 21 to September 2026 F 25; September 2026 M 28 to October 2026 F 2; October 2026 M 5 to October 2026 F 9; October 2026 M 12 to October 2026 F 16; October 2026 M 19 to October 2026 F 23; October 2026 M 26 to October 2026 F 30; Nov 2026 M 2 to Nov 2026 W 4
Order History & Admin Orders | 2 | 2026-08-23 | 2026-08-24 |  | complete | [107 empty] | complete |  | 2026-08-24 | 2026-08-23 | 2 | Order History & Admin Orders | bar: August 2026 S 23 to August 2026 M 24
Sprint 3: Payments & OTP Security | 14 | 2026-08-25 | 2026-09-07 | Sprint 3 | complete | August 2026 T 25: Sprint 3: Payments & OTP Security | complete | Sprint 3 | 2026-09-07 | 2026-08-25 | 14 | Sprint 3: Payments & OTP Security
Razorpay Payment Integration | 3 | 2026-08-25 | 2026-08-27 |  | complete | [107 empty] | complete |  | 2026-08-27 | 2026-08-25 | 3 | Razorpay Payment Integration | bar: August 2026 T 25 to August 2026 T 27
COD Checkout with Risk-Based OTP | 3 | 2026-08-28 | 2026-08-30 |  | complete | [107 empty] | complete |  | 2026-08-30 | 2026-08-28 | 3 | COD Checkout with Risk-Based OTP | bar: July 2026 T 21 to July 2026 F 24; July 2026 M 27 to July 2026 F 31; August 2026 M 3 to August 2026 F 7; August 2026 M 10 to August 2026 F 14; August 2026 M 17 to August 2026 F 21; August 2026 M 24 to September 2026 F 4; September 2026 M 7 to September 2026 F 11; September 2026 M 14 to September 2026 F 18; September 2026 M 21 to September 2026 F 25; September 2026 M 28 to October 2026 F 2; October 2026 M 5 to October 2026 F 9; October 2026 M 12 to October 2026 F 16; October 2026 M 19 to October 2026 F 23; October 2026 M 26 to October 2026 F 30; Nov 2026 M 2 to Nov 2026 W 4
OTP Engine (Hash, Expiry, Retries) | 2 | 2026-08-31 | 2026-09-01 |  | complete | [107 empty] | complete |  | 2026-09-01 | 2026-08-31 | 2 | OTP Engine (Hash, Expiry, Retries) | bar: August 2026 M 31 to September 2026 T 1
Email Delivery (Nodemailer) | 2 | 2026-09-02 | 2026-09-03 |  | complete | [107 empty] | complete |  | 2026-09-03 | 2026-09-02 | 2 | Email Delivery (Nodemailer) | bar: July 2026 T 21 to July 2026 F 24; July 2026 M 27 to July 2026 F 31; August 2026 M 3 to August 2026 F 7; August 2026 M 10 to August 2026 F 14; August 2026 M 17 to August 2026 F 21; August 2026 M 24 to August 2026 F 28; August 2026 M 31 to September 2026 F 4; September 2026 M 7 to September 2026 F 11; September 2026 M 14 to September 2026 F 18; September 2026 M 21 to September 2026 F 25; September 2026 M 28 to October 2026 F 2; October 2026 M 5 to October 2026 F 9; October 2026 M 12 to October 2026 F 16; October 2026 M 19 to October 2026 F 23; October 2026 M 26 to October 2026 F 30; Nov 2026 M 2 to Nov 2026 W 4
OTP Verification UI Screens | 2 | 2026-09-04 | 2026-09-05 |  | complete | [107 empty] | complete |  | 2026-09-05 | 2026-09-04 | 2 | OTP Verification UI Screens | bar: September 2026 F 4 to September 2026 S 5
Refund & Payment Status Handling | 2 | 2026-09-06 | 2026-09-07 |  | complete | [107 empty] | complete |  | 2026-09-07 | 2026-09-06 | 2 | Refund & Payment Status Handling | bar: July 2026 T 21 to July 2026 F 24; July 2026 M 27 to July 2026 F 31; August 2026 M 3 to August 2026 F 7; August 2026 M 10 to August 2026 F 14; August 2026 M 17 to August 2026 F 21; August 2026 M 24 to August 2026 F 28; August 2026 M 31 to September 2026 F 4; September 2026 S 6 to September 2026 F 11; September 2026 M 14 to September 2026 F 18; September 2026 M 21 to September 2026 F 25; September 2026 M 28 to October 2026 F 2; October 2026 M 5 to October 2026 F 9; October 2026 M 12 to October 2026 F 16; October 2026 M 19 to October 2026 F 23; October 2026 M 26 to October 2026 F 30; Nov 2026 M 2 to Nov 2026 W 4
Sprint 4: Blue AI – Detection & Trust | 14 | 2026-09-08 | 2026-09-21 | Sprint 4 | complete | September 2026 T 8: Sprint 4: Blue AI – Detection & Trust | complete | Sprint 4 | 2026-09-21 | 2026-09-08 | 14 | Sprint 4: Blue AI – Detection & Trust
User Activity Logging & Baseline | 2 | 2026-09-08 | 2026-09-09 |  | complete | [107 empty] | complete |  | 2026-09-09 | 2026-09-08 | 2 | User Activity Logging & Baseline | bar: July 2026 T 21 to July 2026 F 24; July 2026 M 27 to July 2026 F 31; August 2026 M 3 to August 2026 F 7; August 2026 M 10 to August 2026 F 14; August 2026 M 17 to August 2026 F 21; August 2026 M 24 to August 2026 F 28; August 2026 M 31 to September 2026 F 4; September 2026 M 7 to September 2026 F 11; September 2026 M 14 to September 2026 F 18; September 2026 M 21 to September 2026 F 25; September 2026 M 28 to October 2026 F 2; October 2026 M 5 to October 2026 F 9; October 2026 M 12 to October 2026 F 16; October 2026 M 19 to October 2026 F 23; October 2026 M 26 to October 2026 F 30; Nov 2026 M 2 to Nov 2026 W 4
Anomaly Rules Engine (Core Rules) | 4 | 2026-09-10 | 2026-09-13 |  | complete | [107 empty] | complete |  | 2026-09-13 | 2026-09-10 | 4 | Anomaly Rules Engine (Core Rules) | bar: September 2026 T 10 to September 2026 S 13
Payment & OTP Failure Rules | 2 | 2026-09-14 | 2026-09-15 |  | complete | [107 empty] | complete |  | 2026-09-15 | 2026-09-14 | 2 | Payment & OTP Failure Rules | bar: July 2026 T 21 to July 2026 F 24; July 2026 M 27 to July 2026 F 31; August 2026 M 3 to August 2026 F 7; August 2026 M 10 to August 2026 F 14; August 2026 M 17 to August 2026 F 21; August 2026 M 24 to August 2026 F 28; August 2026 M 31 to September 2026 F 4; September 2026 M 7 to September 2026 F 11; September 2026 M 14 to September 2026 F 18; September 2026 M 21 to September 2026 F 25; September 2026 M 28 to October 2026 F 2; October 2026 M 5 to October 2026 F 9; October 2026 M 12 to October 2026 F 16; October 2026 M 19 to October 2026 F 23; October 2026 M 26 to October 2026 F 30; Nov 2026 M 2 to Nov 2026 W 4
Trust Score & Auto-Block Logic | 2 | 2026-09-16 | 2026-09-17 |  | complete | [107 empty] | complete |  | 2026-09-17 | 2026-09-16 | 2 | Trust Score & Auto-Block Logic | bar: September 2026 W 16 to September 2026 T 17
Explainable Thoughts & Blue Logs | 2 | 2026-09-18 | 2026-09-19 |  | complete | [107 empty] | complete |  | 2026-09-19 | 2026-09-18 | 2 | Explainable Thoughts & Blue Logs | bar: July 2026 T 21 to July 2026 F 24; July 2026 M 27 to July 2026 F 31; August 2026 M 3 to August 2026 F 7; August 2026 M 10 to August 2026 F 14; August 2026 M 17 to August 2026 F 21; August 2026 M 24 to August 2026 F 28; August 2026 M 31 to September 2026 F 4; September 2026 M 7 to September 2026 F 11; September 2026 M 14 to September 2026 S 19; September 2026 M 21 to September 2026 F 25; September 2026 M 28 to October 2026 F 2; October 2026 M 5 to October 2026 F 9; October 2026 M 12 to October 2026 F 16; October 2026 M 19 to October 2026 F 23; October 2026 M 26 to October 2026 F 30; Nov 2026 M 2 to Nov 2026 W 4
Category-Based Recommendations | 2 | 2026-09-20 | 2026-09-21 |  | complete | [107 empty] | complete |  | 2026-09-21 | 2026-09-20 | 2 | Category-Based Recommendations | bar: September 2026 S 20 to September 2026 M 21
Sprint 5: Red AI, Deals & Dashboards | 14 | 2026-09-22 | 2026-10-05 | Sprint 5 | complete | September 2026 T 22: Sprint 5: Red AI, Deals & Dashboards | complete | Sprint 5 | 2026-10-05 | 2026-09-22 | 14 | Sprint 5: Red AI, Deals & Dashboards
Red AI Brute-Force & Rapid-Fire | 3 | 2026-09-22 | 2026-09-24 |  | complete | [107 empty] | complete |  | 2026-09-24 | 2026-09-22 | 3 | Red AI Brute-Force & Rapid-Fire | bar: September 2026 T 22 to September 2026 T 24
Qty Tampering & OTP-Guess Attacks | 2 | 2026-09-25 | 2026-09-26 |  | complete | [107 empty] | complete |  | 2026-09-26 | 2026-09-25 | 2 | Qty Tampering & OTP-Guess Attacks | bar: July 2026 T 21 to July 2026 F 24; July 2026 M 27 to July 2026 F 31; August 2026 M 3 to August 2026 F 7; August 2026 M 10 to August 2026 F 14; August 2026 M 17 to August 2026 F 21; August 2026 M 24 to August 2026 F 28; August 2026 M 31 to September 2026 F 4; September 2026 M 7 to September 2026 F 11; September 2026 M 14 to September 2026 F 18; September 2026 M 21 to September 2026 S 26; September 2026 M 28 to October 2026 F 2; October 2026 M 5 to October 2026 F 9; October 2026 M 12 to October 2026 F 16; October 2026 M 19 to October 2026 F 23; October 2026 M 26 to October 2026 F 30; Nov 2026 M 2 to Nov 2026 W 4
Blue Dynamic Deal Engine | 3 | 2026-09-27 | 2026-09-29 |  | complete | [107 empty] | complete |  | 2026-09-29 | 2026-09-27 | 3 | Blue Dynamic Deal Engine | bar: September 2026 S 27 to September 2026 T 29
Admin Dashboard UI Design | 2 | 2026-09-30 | 2026-10-01 |  | complete | [107 empty] | complete |  | 2026-10-01 | 2026-09-30 | 2 | Admin Dashboard UI Design | bar: July 2026 T 21 to July 2026 F 24; July 2026 M 27 to July 2026 F 31; August 2026 M 3 to August 2026 F 7; August 2026 M 10 to August 2026 F 14; August 2026 M 17 to August 2026 F 21; August 2026 M 24 to August 2026 F 28; August 2026 M 31 to September 2026 F 4; September 2026 M 7 to September 2026 F 11; September 2026 M 14 to September 2026 F 18; September 2026 M 21 to September 2026 F 25; September 2026 M 28 to October 2026 F 2; October 2026 M 5 to October 2026 F 9; October 2026 M 12 to October 2026 F 16; October 2026 M 19 to October 2026 F 23; October 2026 M 26 to October 2026 F 30; Nov 2026 M 2 to Nov 2026 W 4
Blue Logs & Analytics Dashboard | 2 | 2026-10-02 | 2026-10-03 |  | complete | [107 empty] | complete |  | 2026-10-03 | 2026-10-02 | 2 | Blue Logs & Analytics Dashboard | bar: October 2026 F 2 to October 2026 S 3
Red vs Blue Simulation Runs | 2 | 2026-10-04 | 2026-10-05 |  | complete | [107 empty] | complete |  | 2026-10-05 | 2026-10-04 | 2 | Red vs Blue Simulation Runs | bar: July 2026 T 21 to July 2026 F 24; July 2026 M 27 to July 2026 F 31; August 2026 M 3 to August 2026 F 7; August 2026 M 10 to August 2026 F 14; August 2026 M 17 to August 2026 F 21; August 2026 M 24 to August 2026 F 28; August 2026 M 31 to September 2026 F 4; September 2026 M 7 to September 2026 F 11; September 2026 M 14 to September 2026 F 18; September 2026 M 21 to September 2026 F 25; September 2026 M 28 to October 2026 F 2; October 2026 S 4 to October 2026 F 9; October 2026 M 12 to October 2026 F 16; October 2026 M 19 to October 2026 F 23; October 2026 M 26 to October 2026 F 30; Nov 2026 M 2 to Nov 2026 W 4
Sprint 6: Testing & Deployment | 14 | 2026-10-06 | 2026-10-19 | Sprint 6 | complete | October 2026 T 6: Sprint 6: Testing & Deployment | complete | Sprint 6 | 2026-10-19 | 2026-10-06 | 14 | Sprint 6: Testing & Deployment
Unit Testing (All Modules) | 3 | 2026-10-06 | 2026-10-08 |  | complete | [107 empty] | complete |  | 2026-10-08 | 2026-10-06 | 3 | Unit Testing (All Modules) | bar: July 2026 T 21 to July 2026 F 24; July 2026 M 27 to July 2026 F 31; August 2026 M 3 to August 2026 F 7; August 2026 M 10 to August 2026 F 14; August 2026 M 17 to August 2026 F 21; August 2026 M 24 to August 2026 F 28; August 2026 M 31 to September 2026 F 4; September 2026 M 7 to September 2026 F 11; September 2026 M 14 to September 2026 F 18; September 2026 M 21 to September 2026 F 25; September 2026 M 28 to October 2026 F 2; October 2026 M 5 to October 2026 F 9; October 2026 M 12 to October 2026 F 16; October 2026 M 19 to October 2026 F 23; October 2026 M 26 to October 2026 F 30; Nov 2026 M 2 to Nov 2026 W 4
Integration Testing | 3 | 2026-10-09 | 2026-10-11 |  | complete | [107 empty] | complete |  | 2026-10-11 | 2026-10-09 | 3 | Integration Testing | bar: October 2026 F 9 to October 2026 S 11
Security Testing (Red AI Suite) | 3 | 2026-10-12 | 2026-10-14 |  | complete | [107 empty] | complete |  | 2026-10-14 | 2026-10-12 | 3 | Security Testing (Red AI Suite) | bar: July 2026 T 21 to July 2026 F 24; July 2026 M 27 to July 2026 F 31; August 2026 M 3 to August 2026 F 7; August 2026 M 10 to August 2026 F 14; August 2026 M 17 to August 2026 F 21; August 2026 M 24 to August 2026 F 28; August 2026 M 31 to September 2026 F 4; September 2026 M 7 to September 2026 F 11; September 2026 M 14 to September 2026 F 18; September 2026 M 21 to September 2026 F 25; September 2026 M 28 to October 2026 F 2; October 2026 M 5 to October 2026 F 9; October 2026 M 12 to October 2026 F 16; October 2026 M 19 to October 2026 F 23; October 2026 M 26 to October 2026 F 30; Nov 2026 M 2 to Nov 2026 W 4
User Acceptance Testing (UAT) | 2 | 2026-10-15 | 2026-10-16 |  | complete | [107 empty] | complete |  | 2026-10-16 | 2026-10-15 | 2 | User Acceptance Testing (UAT) | bar: October 2026 T 15 to October 2026 F 16
Bug Fixes & Rule Tuning | 2 | 2026-10-17 | 2026-10-18 |  | complete | [107 empty] | complete |  | 2026-10-18 | 2026-10-17 | 2 | Bug Fixes & Rule Tuning | bar: July 2026 T 21 to July 2026 F 24; July 2026 M 27 to July 2026 F 31; August 2026 M 3 to August 2026 F 7; August 2026 M 10 to August 2026 F 14; August 2026 M 17 to August 2026 F 21; August 2026 M 24 to August 2026 F 28; August 2026 M 31 to September 2026 F 4; September 2026 M 7 to September 2026 F 11; September 2026 M 14 to September 2026 F 18; September 2026 M 21 to September 2026 F 25; September 2026 M 28 to October 2026 F 2; October 2026 M 5 to October 2026 F 9; October 2026 M 12 to October 2026 F 23; October 2026 M 26 to October 2026 F 30; Nov 2026 M 2 to Nov 2026 W 4
Production Deployment | 1 | 2026-10-19 | 2026-10-19 |  | complete | [107 empty] | complete |  | 2026-10-19 | 2026-10-19 | 1 | Production Deployment | bar: October 2026 M 19
Buffer & Final Review | 16 | 2026-10-20 | 2026-11-04 | Buffer | in progress | October 2026 T 20: Buffer & Final Review | in progress | Buffer | 2026-11-04 | 2026-10-20 | 16 | Buffer & Final Review
System Performance Review | 1 | 2026-10-20 | 2026-10-20 |  | complete | [107 empty] | complete |  | 2026-10-20 | 2026-10-20 | 1 | System Performance Review | bar: October 2026 T 20
Stakeholder Demo (Red vs Blue) | 1 | 2026-10-21 | 2026-10-21 |  | complete | [107 empty] | complete |  | 2026-10-21 | 2026-10-21 | 1 | Stakeholder Demo (Red vs Blue) | bar: July 2026 T 21 to July 2026 F 24; July 2026 M 27 to July 2026 F 31; August 2026 M 3 to August 2026 F 7; August 2026 M 10 to August 2026 F 14; August 2026 M 17 to August 2026 F 21; August 2026 M 24 to August 2026 F 28; August 2026 M 31 to September 2026 F 4; September 2026 M 7 to September 2026 F 11; September 2026 M 14 to September 2026 F 18; September 2026 M 21 to September 2026 F 25; September 2026 M 28 to October 2026 F 2; October 2026 M 5 to October 2026 F 9; October 2026 M 12 to October 2026 F 16; October 2026 M 19 to October 2026 F 23; October 2026 M 26 to October 2026 F 30; Nov 2026 M 2 to Nov 2026 W 4
Final Documentation | 2 | 2026-10-22 | 2026-10-23 |  | complete | [107 empty] | complete |  | 2026-10-23 | 2026-10-22 | 2 | Final Documentation | bar: October 2026 T 22 to October 2026 F 23
Post-Launch Monitoring | 3 | 2026-10-24 | 2026-10-26 |  | complete | [107 empty] | complete |  | 2026-10-26 | 2026-10-24 | 3 | Post-Launch Monitoring | bar: July 2026 T 21 to July 2026 F 24; July 2026 M 27 to July 2026 F 31; August 2026 M 3 to August 2026 F 7; August 2026 M 10 to August 2026 F 14; August 2026 M 17 to August 2026 F 21; August 2026 M 24 to August 2026 F 28; August 2026 M 31 to September 2026 F 4; September 2026 M 7 to September 2026 F 11; September 2026 M 14 to September 2026 F 18; September 2026 M 21 to September 2026 F 25; September 2026 M 28 to October 2026 F 2; October 2026 M 5 to October 2026 F 9; October 2026 M 12 to October 2026 F 16; October 2026 M 19 to October 2026 F 30; Nov 2026 M 2 to Nov 2026 W 4
Bug Fixes & Hotfixes | 2 | 2026-10-27 | 2026-10-28 |  | planned | [107 empty] | planned |  | 2026-10-28 | 2026-10-27 | 2 | Bug Fixes & Hotfixes | bar: October 2026 T 27 to October 2026 W 28
User Feedback Collection | 2 | 2026-10-29 | 2026-10-30 |  | planned | [107 empty] | planned |  | 2026-10-30 | 2026-10-29 | 2 | User Feedback Collection | bar: July 2026 T 21 to July 2026 F 24; July 2026 M 27 to July 2026 F 31; August 2026 M 3 to August 2026 F 7; August 2026 M 10 to August 2026 F 14; August 2026 M 17 to August 2026 F 21; August 2026 M 24 to August 2026 F 28; August 2026 M 31 to September 2026 F 4; September 2026 M 7 to September 2026 F 11; September 2026 M 14 to September 2026 F 18; September 2026 M 21 to September 2026 F 25; September 2026 M 28 to October 2026 F 2; October 2026 M 5 to October 2026 F 9; October 2026 M 12 to October 2026 F 16; October 2026 M 19 to October 2026 F 23; October 2026 M 26 to October 2026 F 30; Nov 2026 M 2 to Nov 2026 W 4
Project Closure | 1 | 2026-10-31 | 2026-10-31 |  | planned | [107 empty] | planned |  | 2026-10-31 | 2026-10-31 | 1 | Project Closure | bar: October 2026 S 31
System Handover & Sign-Off | 2 | 2026-11-01 | 2026-11-02 |  | planned | [107 empty] | planned |  | 2026-11-02 | 2026-11-01 | 2 | System Handover & Sign-Off | bar: July 2026 T 21 to July 2026 F 24; July 2026 M 27 to July 2026 F 31; August 2026 M 3 to August 2026 F 7; August 2026 M 10 to August 2026 F 14; August 2026 M 17 to August 2026 F 21; August 2026 M 24 to August 2026 F 28; August 2026 M 31 to September 2026 F 4; September 2026 M 7 to September 2026 F 11; September 2026 M 14 to September 2026 F 18; September 2026 M 21 to September 2026 F 25; September 2026 M 28 to October 2026 F 2; October 2026 M 5 to October 2026 F 9; October 2026 M 12 to October 2026 F 16; October 2026 M 19 to October 2026 F 23; October 2026 M 26 to October 2026 F 30; Nov 2026 S 1 to Nov 2026 W 4
Final Project Report Submission | 2 | 2026-11-03 | 2026-11-04 |  | planned | [107 empty] | planned |  | 2026-11-04 | 2026-11-03 | 2 | Final Project Report Submission | bar: Nov 2026 T 3 to Nov 2026 W 4
Legend: | [5 empty] | July 2026 T 21: Sprint Header; July 2026 F 31: Dev / Backend Task; August 2026 W 12: UI / Design Task; August 2026 M 24: Buffer Phase; September 2026 T 3: Weekend; September 2026 S 12: Status as of:; September 2026 M 21: 2026-10-26 | AIvsAI-SOC ¦ Red vs Blue AI ¦ Jul 21 – Nov 4, 2026
Formulas:
Start Date = MIN([Start Date, row below]:D9)
Start Date = [Start Date]
End Date = MAX([End Date, row below]:E9)
End Date = [End Date]